## Sheet1
Project Digital Storm
Start Date | 2023-08-14
End Date | 2023-11-13
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Description
Begin Day | August 14 | August 20 | August 27 | September 03 | September 10 | September 17 | September 24 | October 01 | October 08 | October 15 | October 22 | October 29 | November 05
Phase One | Recruitment | [5 empty] | Milestone1 | [5 empty] | Project End
Project Plan
Team Plan
Phase Two |  |  |  |  | Write Requirements: assigned to Elowen Whitethorn, Finnian Ironclad
Quality Assurance Plan: assigned to Seraphina Stormrider
Phase Three |  |  |  |  | Architecture Design Plan: assigned to Rowan Emberblade
Development: assigned to Lysandra Moonshadow
Integration Test Plan: assigned to Orion Stonewall
Quality Assurance Confirmation: assigned to Lyric Starcaster
Notes or Comments: